SENTINEL-VSC

Capstone Project Evaluation & 20-Day Completion Plan

Prepared as a senior project evaluator's assessment — based on direct inspection of the repository (clone, compile, and code read), not the README alone.

# 1. Executive Summary

Sentinel-VSC is further along than most capstones at the 20-day mark. The core engine — SAST rules, the Anthropic-backed LLM critic, the secret/PII shield, and the VS Code integration layer (CodeLens, sidebar, tree views, status bar) — is real, wired together, and compiles cleanly with zero TypeScript errors.

However, several things the README and architecture diagram describe do not exist yet or are silently broken: packaging will fail today, there is no automated test suite, and one core feature (fix diff preview) is likely non-functional. These are exactly the kind of gaps an evaluator finds by clicking buttons, not by reading prose — so closing them is the priority for the next 20 days.

# 2. Current State — Verified by Direct Inspection

The team cloned and compiled the repository, ran npm install, and read every source file rather than relying on the README's claims. Findings:

| Component | Status | Evidence |
| --- | --- | --- |
| Extension activation, commands, providers | Done | Wired up in extension.ts — sidebar, tree views, CodeLens, status bar, all 4 commands |
| SAST engine | Working, overstated | 19 regex rules, not “20+”. 11 rules JS/TS-only; Java/Go/Ruby/PHP get ~1 rule each |
| LLM Security Critic | Working, needs check | Real Anthropic API call + JSON schema prompting; hardcoded model string needs verifying |
| Secret Shield | Done | Real regex patterns for AWS/Stripe/GitHub/JWT; reveal/remask timer logic works |
| Grading + OWASP coverage | Done | Clean A–F scoring, dedup logic, content-hash caching |
| Compiles / installs | Confirmed | npm install && npx tsc -p ./ → zero errors |
| Packaging (.vsix) | Broken | assets/icon.png and assets/sentinel-icon.svg referenced but missing — vsce package fails |
| Automated tests | Missing | package.json test script points to out/test/runTest.js, which doesn't exist; only 2 manual fixture files |
| Fix diff preview | Likely broken | sentinel-fix: URI has no registered TextDocumentContentProvider |
| LICENSE file | Missing | README claims MIT, no LICENSE file in repo |
| .vscode/launch.json | Missing | README says “press F5” but no launch config exists |
| CI/CD | Missing | No GitHub Actions workflow |

# 3. Concrete Bugs & Gaps (priority order)

- Packaging will fail today — package.json references assets/icon.png and assets/sentinel-icon.svg, neither of which exists in the repo. Running npm run package (vsce) will error out, blocking the “pre-built VSIX” install path promised in the README.

- No automated tests exist — package.json's test script points to ./out/test/runTest.js and the README's architecture diagram claims a test/suite/ directory, but neither exists. Only two manual fixture files (vulnerable-auth.js, secure-auth.js, 126 lines total) are present, with nothing wired to assert pass/fail.

- Fix diff preview is likely broken — showFixPreviewDiff() opens a sentinel-fix: URI via vscode.diff, but no TextDocumentContentProvider is registered for that scheme anywhere in the code. Clicking “Preview” on a fix probably shows an empty or errored diff.

- SAST rule coverage is uneven — 19 rules total (not “20+” as claimed). 11 rules are JS/TS-only; Java, Go, Ruby, and PHP each get roughly one rule, despite all being listed as “supported languages.”

- LLM critic model string needs verification — the hardcoded model ID should be confirmed as a real, current Anthropic model before demo day, or the LLM critic will silently never return results.

- No LICENSE file, despite the README declaring MIT.

- No .vscode/launch.json — the README instructs contributors to “press F5,” but there is no launch configuration for VS Code to run.

- No CI/CD — no GitHub Actions workflow exists to run compile/test on push.

# 4. 20-Day Plan — Five-Person Team

Work is split into five parallel tracks so all five members are productive from day one, plus three time-boxed phases so the team converges toward a working, demo-ready extension rather than five people polishing in isolation. Assign a name to each track below based on who already knows that part of the codebase best.

| Track | Owns | Responsibilities |
| --- | --- | --- |
| Track 1 | Packaging & Release | Fix missing assets (icon.png, sentinel-icon.svg), get vsce package producing a working .vsix, add LICENSE and .vscode/launch.json, do a clean-install test on a fresh VS Code profile |
| Track 2 | Core Bug Fixes | Register a TextDocumentContentProvider for the sentinel-fix: scheme and get “Preview” actually working; verify/replace the LLM critic's model string; improve error messaging when the API key is missing or invalid |
| Track 3 | SAST Rule Expansion | Add rules for Java, Go, Ruby, and PHP to close the coverage gap between the README's claims and the actual rule set; keep OWASP category mapping consistent with existing rules |
| Track 4 | Test Suite & CI | Stand up test/suite/ using the already-installed @vscode/test-electron dependency; write unit tests for sastEngine.ts and secretShield.ts first (pure logic, easiest to test); add a GitHub Actions workflow (npm ci && npm run compile && npm test) |
| Track 5 | Metrics, Report & Demo | Build 6–8 additional sample files per language beyond the current 2; record real detection/false-positive numbers; update Capstone_final_Report.docx with true rule counts and a known-limitations section; own the demo script and rehearsal |

Phase 1 — Fix what's silently broken   (Days 1–4)

- Track 1: assets + LICENSE + launch.json; confirm a real .vsix builds

- Track 2: fix the diff-preview provider; test “Fix with Sentinel” end-to-end on both existing sample files

- Track 2/3: verify the LLM critic's model ID against a real current Anthropic model

- Track 4: scaffold test/suite/ and get the first unit test running (even a trivial one) so the harness itself is proven

- Track 5: draft the known-limitations section for the report using this evaluation as the source

Phase 2 — Close the real coverage gap   (Days 5–12)

- Track 3: add SAST rules for Java, Go, Ruby, PHP — this is the single biggest gap between what's advertised and what's implemented

- Track 4: write integration tests running the orchestrator against the expanded sample set; record actual detection and false-positive rates per language

- Track 4: get CI running on every push

- Track 1/2: address any packaging or bug-fix follow-ups surfaced by the new tests

- Track 5: keep the report's numbers in sync with what Track 3/4 are actually producing, rather than writing it at the end from memory

Phase 3 — Polish and demo readiness   (Days 13–17)

- Track 1: package the final .vsix and do one more full clean-install test

- Track 5: run the full workflow (scan → grade → fix → apply → re-scan → reveal secret) on a real small vulnerable app, not just toy samples, and capture before/after numbers

- Track 5: finalize Capstone_final_Report.docx — every claim in it should match what the extension actually does when you click the button

- All tracks: cross-check the README against the real feature set and correct any remaining overstatements (e.g. rule count, language coverage)

Phase 4 — Buffer and rehearsal   (Days 18–20)

- Freeze the code

- Record a full demo run-through as a video backup in case the live environment misbehaves

- Dry-run the presentation as a team; assign who narrates which track's work

# 5. What Evaluators Will Actually Test

Based on the gap between the README and the working code, expect an evaluator to: install the extension fresh, open the sample files, click every button in the sidebar and CodeLens, try “Fix with Sentinel” and its Preview option, and check whether the languages you claim to support actually produce meaningful results. Closing the Phase 1 and Phase 2 items above directly addresses what a hands-on evaluation will surface.